## Overview
AMAN GOLD - DELIVERY PACK (retrospective)
Generated from the actual session evidence. Read the honesty notes before using the numbers.
NOTE |  | Sprint tickets and QA stories were written AFTER the work as a retrospective; no live Jira project existed during the build.
NOTE |  | No Figma file was created. The design flow is a Claude Design canvas (screens + prototype links).
NOTE |  | Test results come from scripted browser checks run by Claude, not from a human QA team. Cases not run are marked 'Not executed'.
NOTE |  | Times come from file-system timestamps. 'Elapsed' includes time spent waiting for the PM; active build time is shorter. Human-equivalent effort is an ESTIMATE.
Metric | Value | Detail
Epics / stories / tasks (delivered) | 4 / 21 / 23 | Sprint Backlog sheet
Story points delivered (ESTIMATE) | 108 | Stories only; tasks roll up
QA stories / tasks (new, for testing team) | 7 / 13 | QA Backlog sheet
Test cases | 70 | Test Cases sheet
Pass | 45 | Executed and passed
Failed then fixed | 7 | Found a defect, fixed, re-verified
Not executed | 18 | Still to run (see QA Backlog)
Defects logged | 13 | Defects sheet
Change requests / decisions | 19 | Change Requests sheet
Business Case Lab size | 30 files / ~1,600 lines | 2026-09-20 21:34 to 2026-09-21 17:02
Customer Prototype size | 36 files / ~1,846 lines | 2026-09-21 22:39 to 2026-09-22 02:50 (incl. 4 docs)
Core prototype code generation | 8 minutes | 22:39-22:47, config + services + all screens
Debugging and fixing | about 40 minutes | DEF-01..03 about 14 min; daylight-saving defect about 25 min; plus small fixes

## Timeline & Effort
Phase | Start | End | Elapsed | What happened | Evidence
Business case: research + first build | 2026-09-20 21:34 | 2026-09-20 22:17 | 0h 43m | Core Lab source written in bursts (types, research data, model, 5 agents, debate, report). 30 files, ~1,600 lines. | File creation times
Business case: PM changes applied (prepaid card, CAC 10, in-house) | 2026-09-21 17:01 | 2026-09-21 17:02 | not measurable | Model, agents, risks and decision logic re-wired after each PM update. File times only show the last edits (17:01-17:02); the start of these rounds cannot be read from the file system. | File modified times
Prototype: Phase 1 discovery (assumptions, conflicts, MVP scope) | 2026-09-21 ~22:00 | 2026-09-21 22:39 | n/a | Analysis + 4 decisions from PM. No code. | Conversation
Prototype: core code generation (config, services, 10 screens) | 2026-09-21 22:39 | 2026-09-21 22:47 | 0h 8m | Foundations + all screens + first 3 docs created in one burst. ~1,850 lines total by the end of the project. | File creation times
Prototype: first verification + CR-01/02 (real price, 0.1 g step) | 2026-09-21 22:47 | 2026-09-21 23:34 | 0h 47m | Scripted browser run of onboarding, buy, sell, edge cases; then price anchor and 0.1 g step changes. | File modified times
Waiting for PM feedback (screenshots) | 2026-09-21 23:34 | 2026-09-22 01:59 | 2h 25m | No code changes. Idle from the build's point of view. | File modified times
Defect cycle: duplicate orders / balance drift (DEF-01..03) + palette (CR-03) | 2026-09-22 01:59 | 2026-09-22 02:13 | 0h 14m | Reproduced (1 buy became 3), root-caused, store rewritten, re-tested; palette applied. | File modified times
CR-04/05/06/07 Portfolio + Daily P&L + real-price ledger | 2026-09-22 02:13 | 2026-09-22 02:39 | 0h 26m | Calendar, cumulative chart, real Sept price data, DST defect found and fixed. | File modified times
CR-10 New-customer onboarding: code + scripted tests | 2026-09-22 03:12 | 2026-09-22 03:14 | 2 min 17 s | Scenario control, 10-step OnboardingNew flow, gating, prepaid card + top-up; scripted browser walk of all 10 steps, first buy, profile and two regressions (11 test cases run). | Command timestamps
CR-10 docs, tickets, test cases, design frames and workbook | 2026-09-22 03:14 | 2026-09-22 03:17 | 2 min 43 s | PRD and flow doc updated, story AG-21 + 5 tasks, QA-7, TC-060..073, CR-10, branch diagram + 8 canvas frames. | Command timestamps
CR-08/09 P&L card clarified then removed | 2026-09-22 02:39 | 2026-09-22 02:50 | 0h 11m | Two small UI edits and re-verification. | File modified times
Effort summary | Wall-clock (real) | Files | Lines | Human-equivalent (ESTIMATE, not measured)
Business Case Lab | 20 Sep 21:34 to 21 Sep 17:02 (19h 28m elapsed, mostly waiting for answers); initial code took 43 min, later update rounds are not separately measurable | 30 | 1600 | ESTIMATE: 60-90 person-hours (finance model, 5 agents, research, report)
Customer Prototype (incl. docs) | 21 Sep 22:39 to 22 Sep 02:50 (4h 11m elapsed; ~2h 25m of it waiting for PM) | 36 | 1846 | ESTIMATE: 80-120 person-hours (design, 10+ screens, engine, QA)
CR-10 New-customer onboarding (total) | 2026-09-22 03:17 | 1 | 156 | ESTIMATE: 12-20 person-hours for design, build, tests and documentation
Debugging and fixing | About 14 min for DEF-01..03 plus ~25 min inside the P&L work for the daylight-saving defect; ~40 min total | 0 | 0 | ESTIMATE: 6-10 person-hours incl. reproduction and regression

## Sprint Backlog
Type | ID | Parent | Summary | Acceptance / detail | Points (ESTIMATE) | Status | Sprint | Component
Epic | AG-E1 |  | Business Case Lab (internal decision tool) | Multi-agent, evidence-based business case for Aman Gold |  | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Business case
Story | AG-1 | AG-E1 | As a PM I enter inputs with value, unit, source, type and confidence | Types ACTUAL/EXTERNAL FACT/BENCHMARK/ASSUMPTION/ESTIMATE/UNKNOWN; blank = UNKNOWN; never upgraded | 5 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Task | AG-1.1 | AG-1 | Define data types and input schema | types.ts | 1 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Task | AG-1.2 | AG-1 | Load PM figures as inputs (customers, funnel, pricing, costs) | assumptions.ts | 2 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Task | AG-1.3 | AG-1 | Inputs panel UI (edit value, type, confidence, source) | InputsPanel.tsx | 2 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Story | AG-2 | AG-E1 | As CFO I see revenue, cost, unit economics, scenarios, stress tests, break-even | Formulas traceable to inputs; UNKNOWN never invented | 8 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Task | AG-2.1 | AG-2 | 36-month monthly financial model | financial-model.ts | 3 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Task | AG-2.2 | AG-2 | Conservative / Base / Aggressive scenarios |  | 1 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Task | AG-2.3 | AG-2 | 9 stress tests + sensitivity tornado + break-even solver |  | 3 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Task | AG-2.4 | AG-2 | Number traceability (click a KPI to see inputs and type) | Weakest data type wins | 1 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Story | AG-3 | AG-E1 | As R&D I have sourced market and competitor facts | Every external claim has a source; unknown stays unknown | 5 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Task | AG-3.1 | AG-3 | Web research (Egypt gold demand, FRA statement, Thndr/mngm/Goldady, CAC benchmark, FX) | 11 sources registered | 3 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Research
Task | AG-3.2 | AG-3 | Competitor table, gap analysis, sources registry |  | 2 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Research
Story | AG-4 | AG-E1 | As management I see five agents debate in 7 rounds and reach an evidence-based decision | CEO/CFO/CMO/R&D/Risk; positions can change; decision is a gate, not an average | 13 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Task | AG-4.1 | AG-4 | Five agent modules (deterministic, labelled DEMO AI AGENT) |  | 5 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Task | AG-4.2 | AG-4 | Debate engine rounds 1-7, consensus, decision matrix, risk register |  | 5 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Task | AG-4.3 | AG-4 | Validation plan (6 experiments) and 14-page management report |  | 3 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Story | AG-5 | AG-E1 | As PM I re-run the case when assumptions change (prepaid card, CAC, in-house team) | Agents and decision react; no stale text | 5 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Task | AG-5.1 | AG-5 | Apply CR-BC-01..05 to inputs, model, risks, agents |  | 3 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Task | AG-5.2 | AG-5 | Remove hardcoded text that went stale | Fix for DEF-09 | 2 | Done | Sprint 1 (20-21 Sep 2026): Business Case Lab | Lab
Epic | AG-E2 |  | Product definition | Discovery, decisions and documents |  | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Product
Story | AG-6 | AG-E2 | As PM I get a Phase 1 discovery: assumptions, conflicts, MVP scope | Conflicts C1-C9 listed; 4 decisions confirmed by PM | 3 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Product
Story | AG-7 | AG-E2 | As a team we have a PRD, flows, architecture, assumptions/compliance/risk/roadmap | docs/01-04 (.md) | 5 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Product
Epic | AG-E3 |  | Design | Customer experience and flow |  | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Design
Story | AG-8 | AG-E3 | As a designer I have a clickable screen flow board | Claude Design canvas (Figma file not created) | 3 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Design
Story | AG-9 | AG-E3 | As a brand owner the prototype uses the Aman palette | Gradient #04768D to #64C2D3 (CR-03) | 1 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Design
Epic | AG-E4 |  | Aman Gold customer prototype | Clickable mobile prototype, demo data |  | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Story | AG-10 | AG-E4 | Foundations: config, pricing service, engine, store, seed | No business values in UI; ledger is the single source of truth | 8 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Task | AG-10.1 | AG-10 | product.ts config (spread, fee, limits, quote validity, funding) |  | 1 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Task | AG-10.2 | AG-10 | Pricing service (getCurrentGoldPrice, getHistoricalGoldPrices, buy/sell) | Replaceable by provider API | 2 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Task | AG-10.3 | AG-10 | Transaction engine: quotes, validation, average-cost wallet, cash |  | 3 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Task | AG-10.4 | AG-10 | Atomic store with busy lock and derived balances | Fix for DEF-01..03 | 2 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Story | AG-11 | AG-E4 | Discover and onboard (Home entry, landing, 7-step onboarding) | Account check reuses data; KYC checklist configurable | 8 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Story | AG-12 | AG-E4 | See portfolio value, holdings, price and chart (1D-1Y) | Chart from pricing service; real daily prices 22 Aug-21 Sep 2026 | 5 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Story | AG-13 | AG-E4 | Buy gold in 0.1 g steps (by grams or EGP) with price lock and PIN | Success shows ID and before/after balances | 8 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Story | AG-14 | AG-E4 | Sell gold (by grams or EGP), proceeds to prepaid balance |  | 5 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Story | AG-15 | AG-E4 | Portfolio: allocation donut, today's realized P&L, unrealized P&L, cumulative P&L chart | CR-04/06/09 | 5 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Story | AG-16 | AG-E4 | Daily P&L calendar (realized only, today live) | CR-04/07 | 5 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Story | AG-17 | AG-E4 | Transactions list and detail with before/after cash and gold |  | 3 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Story | AG-18 | AG-E4 | Profile, documents, FAQ, support |  | 2 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Story | AG-19 | AG-E4 | Edge cases and prototype controls (7 states) | Insufficient balance/gold, price changed, failed tx, provider down, KYC incomplete, volatility | 3 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Story | AG-21 | AG-E4 | New-customer onboarding: capture everything when nothing is on file | 10 steps: mobile, code, PIN, personal details, ID, selfie, prepaid card + InstaPay top-up, agreements, done. Demo validations only. Scenario control switches between customer types (CR-10) | 5 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Task | AG-21.1 | AG-21 | Scenario control: existing Aman customer / brand-new customer / existing investor | store mode brandNew, PhoneShell controls | 1 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Task | AG-21.2 | AG-21 | OnboardingNew flow with step gating and 'fill demo data' | OnboardingNew.tsx | 3 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Task | AG-21.3 | AG-21 | Prepaid card issue and first top-up; opening balance from the top-up | Brand-new customer starts with EGP 0 | 1 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype
Task | AG-21.4 | AG-21 | Design: branch diagram + 8 new-customer frames on the flow board | Claude Design canvas | 2 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Design
Task | AG-21.5 | AG-21 | Update PRD, flow doc, tickets, test cases and change log |  | 1 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Product
Story | AG-20 | AG-E4 | Realistic demo ledger on real Egypt prices with win/loss days | 20 transactions, +EGP 307.89 realized in Sep (7 winning / 4 losing days) | 3 | Done | Sprint 2 (21-22 Sep 2026): Customer Prototype | Prototype

## QA Backlog
Type | ID | Parent | Summary | Acceptance / detail | Points (ESTIMATE) | Status | Sprint | Component
Epic | QA-E1 |  | Aman Gold prototype: quality assurance | Independent QA of the prototype and the business-case lab |  | To do | Sprint 3 (proposed) | QA
Story | QA-1 | QA-E1 | As QA I execute all 'Not executed' test cases and record results | All TC rows with result 'Not executed' run by a human on Chrome desktop | 5 | To do | Sprint 3 (proposed) | QA
Task | QA-1.1 | QA-1 | Run edge-case toggles: provider unavailable, KYC incomplete, fail next transaction, volatility banner | TC-035..038 | 2 | To do | Sprint 3 (proposed) | QA
Task | QA-1.2 | QA-1 | Run top-up via InstaPay sheet and quote-expiry (wait 30 s) flows | TC-031b, TC-034 | 1 | To do | Sprint 3 (proposed) | QA
Task | QA-1.3 | QA-1 | Run transaction detail, profile/FAQ, hide-balance, bars view, reload persistence | TC-049..054 | 2 | To do | Sprint 3 (proposed) | QA
Story | QA-2 | QA-E1 | As QA I verify ledger integrity under stress | No duplicate IDs, cash and gold always equal a recomputation from the ledger | 5 | To do | Sprint 3 (proposed) | QA
Task | QA-2.1 | QA-2 | Rapid-tap and double-click tests on every confirm and PIN control | Regression for DEF-01 | 2 | To do | Sprint 3 (proposed) | QA
Task | QA-2.2 | QA-2 | Randomized buy/sell sequences (100+) compared with an independent calculator | Average cost, realized, unrealized, cash | 3 | To do | Sprint 3 (proposed) | QA
Task | QA-2.3 | QA-2 | Boundary tests: 0.1 g, 0.0 g, max order, daily limit, sell everything |  | 2 | To do | Sprint 3 (proposed) | QA
Story | QA-3 | QA-E1 | As QA I validate P&L calendar and charts | Calendar, cumulative chart and portfolio agree at all times, incl. month and daylight-saving boundaries | 3 | To do | Sprint 3 (proposed) | QA
Task | QA-3.1 | QA-3 | Test months boundaries (Oct 2025 to Sep 2026) and daylight-saving change dates | Regression for DEF-04 | 2 | To do | Sprint 3 (proposed) | QA
Story | QA-4 | QA-E1 | As QA I check UI on phone sizes, browsers and accessibility | iPhone 390 px, Android 360 px, Chrome/Safari/Edge, keyboard and contrast | 5 | To do | Sprint 3 (proposed) | QA
Task | QA-4.1 | QA-4 | Visual comparison with Aman Home and the palette |  | 2 | To do | Sprint 3 (proposed) | QA
Story | QA-5 | QA-E1 | As QA I verify data accuracy and labelling | Real daily prices match source; DEMO labels present; no assumption shown as fact | 3 | To do | Sprint 3 (proposed) | QA
Task | QA-5.1 | QA-5 | Cross-check 31 daily prices against the source table and a second site |  | 1 | To do | Sprint 3 (proposed) | QA
Task | QA-5.2 | QA-5 | Check every business-case number can be traced to an input and type | Traceability modal | 2 | To do | Sprint 3 (proposed) | QA
Story | QA-7 | QA-E1 | As QA I verify new-customer onboarding validations and recovery | Every field validation, back navigation and refresh behaviour, plus scenario switching | 5 | To do | Sprint 3 (proposed) | QA
Task | QA-7.1 | QA-7 | Field validation edge cases: short mobile, 13-digit ID, wrong DOB format, short address, mismatched PIN | TC-071 | 2 | To do | Sprint 3 (proposed) | QA
Task | QA-7.2 | QA-7 | Back navigation keeps typed values; refresh mid-flow behaviour agreed with Product | TC-072 | 2 | To do | Sprint 3 (proposed) | QA
Task | QA-7.3 | QA-7 | Skip top-up, then attempt a buy (insufficient balance path) | TC-073 | 1 | To do | Sprint 3 (proposed) | QA
Story | QA-6 | QA-E1 | As QA I test the Business Case Lab what-if sliders and report generation | Sliders recompute; 14-page report locks inputs | 3 | To do | Sprint 3 (proposed) | QA

## Test Cases
ID | Area | Title | Preconditions | Steps | Expected | Actual | Result | Method | Defect | Linked CR
TC-001 | Lab | Default inputs load with value, unit, source, type | Open Lab | Read Inputs tab | 39 inputs each with type and confidence | Inputs rendered with types | Pass | Scripted browser check (Claude), DOM text assertions
TC-002 | Lab | Funnel math (30% x 20% x 10% of 360K MAU) | Default inputs | Run model | 2,160 first buyers | 2,160 buyers | Pass | Node run of the model
TC-003 | Lab | Negative unit margin when gateway 1% and spread 0.5% | Original inputs | Read unit economics | -0.50% per EGP | -0.50% | Pass | Node run + UI
TC-004 | Lab | Aggressive scenario loses more than Base at negative margin | Original inputs | Compare scenarios | Aggressive net < Base net | -42.7M vs -40.9M | Pass | Node run
TC-005 | Lab | Model after PM changes (gateway 0, CAC 10) | Updated inputs | Read dashboard and decision | Margin +0.5%, LTV/CAC 6.5, payback ~2 months, PROCEED WITH CONDITIONS | +0.50%, 6.5, 2.1 months, PROCEED WITH CONDITIONS | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-BC-01/03
TC-006 | Lab | Stress tests after PM changes | Updated inputs | Read stress table | Viability shown per shock | 9 of 9 viable, tiny absolute values | Pass | Scripted browser check (Claude), DOM text assertions
TC-007 | Lab | UNKNOWN inputs are excluded, not invented | Buy/sell ratio blank | Run model | Sell side excluded and flagged | Excluded and listed as UNKNOWN | Pass | Scripted browser check (Claude), DOM text assertions
TC-008 | Lab | Click a KPI to trace it (modal) | Open Lab | Click Revenue tile | Modal with inputs and weakest type | Tile type label seen; modal not opened | Not executed | -
TC-009 | Lab | Generate Management Business Case | Open Lab | Click generate | 12 steps, inputs locked, 14 pages | 15 page blocks incl. cover; last page = decision | Pass | Scripted browser check (Claude), DOM text assertions
TC-010 | Lab | No console errors on load and tab switching | Open Lab | Switch all tabs | No errors | No errors | Pass | Browser console read
TC-011 | Lab | Seven debate rounds render | Open Agents tab | Count round sections | Rounds 1-7 present | All rounds and 6 tables present | Pass | Scripted browser check (Claude), DOM text assertions
TC-012 | Lab | Agents revise positions in round 7 | Updated inputs | Read round 7 | At least one agent changes | CEO changed to VALIDATE FURTHER (original inputs) | Pass | Scripted browser check (Claude), DOM text assertions
TC-013 | Lab | What-if sliders recompute all outputs | Open Financial tab | Move sliders | Outputs update instantly | Not exercised | Not executed | -
TC-014 | Lab | Revenue type label is correct | Default inputs | Read dashboard type | Weakest input type (ESTIMATE) | Showed UNKNOWN | Fail -> Fixed | Scripted browser check (Claude), DOM text assertions | DEF-08
TC-015 | Lab | Agent text follows input changes | Change inputs | Read agent text | No stale numbers or claims | Stale hardcoded text found in several places | Fail -> Fixed | Scripted browser check (Claude), DOM text assertions | DEF-09
TC-020 | Prototype | Home shows Gold strip and tile with price | Open app | Read Home | Gold strip, tile, price per gram | Present, price EGP 7,224 | Pass | Scripted browser check (Claude), DOM text assertions
TC-021 | Prototype | Landing shows price, chart, buy/sell, fees, risk | New customer | Open Gold tile | All blocks visible | All present | Pass | Scripted browser check (Claude), DOM text assertions
TC-022 | Prototype | Onboarding 7 steps to Done | New customer | Walk all steps, any 4-digit OTP, tick agreement | Reaches dashboard | Reached dashboard, empty state | Pass | Scripted browser check (Claude), DOM text assertions
TC-023 | Prototype | Empty dashboard for new customer | After onboarding | Read dashboard | EGP 0, 0.0 g, Sell disabled | As expected | Pass | Scripted browser check (Claude), DOM text assertions
TC-024 | Prototype | Buy by EGP rounds down to 0.1 g step | Buy screen | Enter EGP 2,000 | 0.2 g for EGP 1,451.82, remainder shown | 0.2 g, EGP 548.18 stays in balance | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-02
TC-025 | Prototype | Buy by grams: 0.25 g invalid, 0.5 g valid | Buy screen | Enter 0.25 then use chip 0.5 | Step error; then summary | Error shown; summary shown | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-02
TC-026 | Prototype | Below minimum blocked | Buy screen | EGP 500 by EGP | 'The minimum is 0.1 g.' | Message shown | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-02
TC-027 | Prototype | Order summary content | Buy 0.5 g | Review order | Qty, price, investment, fee 0, total, method, 30 s lock | All shown | Pass | Scripted browser check (Claude), DOM text assertions
TC-028 | Prototype | PIN, processing, success with ID | Order summary | Confirm, enter 1234 | Success with transaction ID | GOLD-000124 shown | Pass | Scripted browser check (Claude), DOM text assertions
TC-029 | Prototype | Success shows before/after gold and cash | After buy | Read success | Balances consistent | Consistent | Pass | Scripted browser check (Claude), DOM text assertions
TC-030 | Prototype | Sell by grams/EGP with percent chips and 'credited to balance' | Holding gold | Sell 50% / 100% | Summary and success show proceeds credited | As expected | Pass | Scripted browser check (Claude), DOM text assertions
TC-031a | Prototype | Insufficient balance message | Existing investor | Buy 30,000 EGP | 'You don't have enough available balance.' + top-up link | Message and link shown | Pass | Scripted browser check (Claude), DOM text assertions
TC-031b | Prototype | InstaPay top-up sheet adds balance | After TC-031a | Tap top-up and choose amount | Balance increases | Sheet not executed | Not executed | -
TC-032 | Prototype | Insufficient gold message | Existing investor | Sell 50 g | 'You don't have enough gold to complete this sale.' | Message shown | Pass | Scripted browser check (Claude), DOM text assertions
TC-033 | Prototype | Price changed when price moves during quote | Open summary | Click +3% then Confirm | 'The gold price has changed...' sheet | Sheet shown | Pass | Scripted browser check (Claude), DOM text assertions
TC-034 | Prototype | Quote expires after 30 s | Open summary | Wait 30 s | Price changed sheet | Countdown seen, expiry not waited | Not executed | -
TC-035 | Prototype | Provider unavailable disables trading | Control on | Open Gold | Banner + Buy/Sell disabled | Not executed | Not executed | -
TC-036 | Prototype | KYC incomplete blocks investing | Control on | Try buy | 'Please complete your information...' | Not executed | Not executed | -
TC-037 | Prototype | Failed transaction screen, balances unchanged | Control on | Complete a buy | 'We couldn't complete your transaction' | Not executed | Not executed | -
TC-038 | Prototype | Volatility banner | Control on | Open trade | Rapid-change warning | Not executed | Not executed | -
TC-039 | Prototype | One order creates exactly one transaction | Existing investor | Buy 0.5 g and tap 5-7 PIN keys | 1 new transaction | Before fix: 3 transactions and +1.5 g. After fix: 1 in each of 3 orders | Fail -> Fixed | Scripted reproduction, then re-run | DEF-01
TC-040 | Prototype | Cash and gold reconcile to the ledger | After trades | Recompute independently | Match | 6.9 g, EGP 36,456.30, average EGP 6,535.91 all match | Pass | Independent recomputation in browser | DEF-02
TC-041 | Prototype | Buy, partial sell, re-buy keeps P&L valid | Existing investor | Run sequence | Average cost and P&L consistent | Consistent; unrealized = (sell - avg) x grams | Pass | Independent recomputation | DEF-03
TC-042 | Prototype | Unrealized P&L formula | Holding 6.9 g | Compare UI with formula | (7,185.71 - 6,535.91) x 6.9 = 4,483.6 | UI +4,484 | Pass | Independent recomputation
TC-043 | Prototype | Calendar month total equals sum of sells | Existing investor | Read September | = sum of sell realized P&L | +307.89 vs 307.91 (rounding) | Pass | Scripted browser check (Claude), DOM text assertions
TC-044 | Prototype | Daily totals reconcile to portfolio total | First P&L design | Sum months vs total | Equal | Short by EGP 50 (a daylight-saving day was mishandled) | Fail -> Fixed | Scripted comparison | DEF-04 | CR-04
TC-045 | Prototype | Today's cell is live | Existing investor | Sell 2.7 g today | Today's row and cell show the sale | -127.09 in row and cell; month +180.80; cumulative +180.80 | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-07
TC-046 | Prototype | Cumulative chart ends at calendar total | Existing investor | Compare | +307.89 | +307.89 | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-06
TC-047 | Prototype | Chart ranges use real daily prices | Dashboard | Read 1W and 1M low/high | 1W 7,136-7,368; 1M 7,105-7,551 | Matches source table | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-05
TC-048 | Prototype | Palette applied | Any screen | Read computed styles | #04768D to #64C2D3; button #04768D | As expected | Pass | Computed style read |  | CR-03
TC-049 | Prototype | Transactions list newest first; detail shows before/after | Existing investor | Open Activity, then a row | List and detail correct | List seen; detail not opened | Not executed | -
TC-050 | Prototype | Profile, documents, FAQ | Any | Open Profile sheets | Content shows | Not exercised | Not executed | -
TC-051 | Prototype | Hide balances (eye) masks values | Portfolio | Tap eye | Values masked | Not exercised | Not executed | -
TC-052 | Prototype | Daily P&L Bars view and day detail sheet | Daily P&L | Switch view, tap a day | Bars and sheet show | Not exercised | Not executed | -
TC-053 | Prototype | Month navigation back to first trade month | Daily P&L | Tap previous until disabled | Ends at Oct 2025 | Reached Oct 2025 | Pass | Scripted browser check (Claude), DOM text assertions
TC-054 | Prototype | State persists after reload | After trades | Reload page | Ledger retained | Not verified | Not executed | -
TC-055 | Prototype | Phone-size layout and other browsers | - | Test 360-390 px, Safari, Edge | Layout intact | Only desktop Chrome pane used | Not executed | -
TC-056 | Prototype | Accessibility: keyboard and contrast | - | Tab through flows | Usable and readable | Not tested | Not executed | -
TC-057 | Prototype | Chart preview for invalid quantity | Buy 0.25 g | Read preview | No misleading rounded quantity | Showed '0.3 g' before fix | Fail -> Fixed | Scripted browser check (Claude), DOM text assertions | DEF-10
TC-058 | Prototype | Calendar cell precision | Daily P&L | Read Sept 16 | +115.59 | Showed +116 before fix | Fail -> Fixed | Scripted browser check (Claude), DOM text assertions | DEF-13
TC-060 | Prototype | Scenario control starts a brand-new customer with nothing on file | Any state | Choose 'Brand-new customer' | Empty profile; landing then new-customer onboarding | New-customer flow shown ('New to Aman?'), no data on file | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-10
TC-061 | Prototype | New-customer steps are gated until valid | Brand-new customer | Walk 10 steps, checking the button at each | Continue disabled until the step is valid | Correctly disabled/enabled at every step | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-10
TC-062 | Prototype | PIN mismatch is blocked with a message | Step 4 | Enter 1234 and 9999 | 'PINs do not match.'; continue disabled | Message shown; disabled | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-10
TC-063 | Prototype | Personal details validation and demo-fill | Step 5 | Empty, then 'Fill demo data' | Disabled when empty; enabled when valid | As expected | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-10
TC-064 | Prototype | ID needs both sides; selfie required | Steps 6-7 | Capture one side, then both; take selfie | Continue only after all captures | As expected | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-10
TC-065 | Prototype | Prepaid card issue and InstaPay top-up | Step 8 | Issue card, choose 10K | Card shown; balance EGP 10,000 | Balance EGP 10,000 | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-10
TC-066 | Prototype | Completion summary and dashboard | Steps 9-10 | Accept terms, View Gold | Masked ID, balance; dashboard greets by name | 'Hi, Sara', ID 2900******4567, EGP 0 gold | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-10
TC-067 | Prototype | First buy from the new customer's balance | After onboarding | Buy 0.5 g | Cash 10,000 to 6,370.31 | EGP 10,000.00 to 6,370.31; gold 0.0 to 0.5 g | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-10
TC-068 | Prototype | Profile shows the captured data | After onboarding | Open Profile | Name, mobile, KYC Complete, card, balance | All shown correctly | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-10
TC-069 | Prototype | Regression: existing-customer onboarding | Existing Aman customer scenario | Start onboarding | Account check with data on file | Account check shown with Ahmed's data | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-10
TC-070 | Prototype | Regression: existing investor scenario | Existing investor scenario | Open Gold | 20 transactions, 5.5 g | 20 transactions, 5.5 g, EGP 39,528 | Pass | Scripted browser check (Claude), DOM text assertions |  | CR-10
TC-071 | Prototype | Field validation edge cases | Step 2, 5 | Short mobile, 13-digit ID, bad DOB, short address | Each blocked with the right hint | Only happy path and PIN mismatch exercised | Not executed | - |  | CR-10
TC-072 | Prototype | Back keeps values; refresh mid-flow | Any step | Go back; reload | Values kept / defined behaviour | Not exercised | Not executed | - |  | CR-10
TC-073 | Prototype | Skip top-up then try to buy | Zero balance | Buy any amount | Insufficient balance with top-up link | Not exercised | Not executed | - |  | CR-10
TC-059 | Prototype | Prototype opens on the right URL | Fresh machine | Open app | Prototype, not Connector Directory | User opened port 3000 (wrong app) | Fail -> Fixed | User report | DEF-06

## Defects
ID | Severity | Found by | Summary | Root cause | Fix | Verified
DEF-01 | High | PM (screenshots 3-4) and Claude reproduction | One order created several transactions; gold balance did not match history | PIN pad accepted taps after the 4th digit and each tap re-submitted the order | Ignore taps after 4th digit; one order at a time (busy lock); checks re-run at commit | Yes (TC-039)
DEF-02 | High | PM (screenshot 2) | Available balance far above starting cash after one losing trade | Cash stored separately from the ledger and updated from stale values | Cash and gold are derived from the ledger, never stored; atomic state updates | Yes (TC-040)
DEF-03 | High | PM (screenshot 1) | Average buy price EGP 18,276 and -60% unrealized P&L | Duplicate sells oversold gold; cost basis stopped shrinking | Wallet cannot sell more than held; P&L replay clamps | Yes (TC-041, 042)
DEF-04 | Medium | Claude (reconciliation check) | Daily P&L totals EGP 50 short of portfolio total | Fixed 24-hour day steps broke at Egypt's daylight-saving change | Calendar-safe date arithmetic (later design uses realized-only) | Yes (TC-044)
DEF-05 | Low | PM | P&L card mixed periods and looked contradictory to Today's Realized | Card showed all-time realized next to today's value without labels | Periods labelled, then card removed (CR-08/09) | Yes
DEF-06 | Low | PM | Prototype link opened the Connector Directory | Two local apps: port 3000 (other) vs 3200 (prototype) | Correct URL communicated; one-click launcher added | Yes
DEF-07 | Low | Claude | Blank page when the dev server stopped | Local dev server process ended | Restarted; launcher .bat provided | Yes
DEF-08 | Low | Claude | Lab revenue tile labelled UNKNOWN | Failure-rate input typed UNKNOWN with value 0 | Typed ASSUMPTION (0%) | Yes (TC-014)
DEF-09 | Medium | Claude | Agent text quoted old numbers after inputs changed | Hardcoded phrases in agents, debate and decision | Replaced with values computed from inputs | Yes (TC-015)
DEF-10 | Low | Claude | Invalid 0.25 g showed rounded '0.3 g' preview | Preview formatted a value that failed validation | Hide preview on step error | Yes (TC-057)
DEF-11 | Low | Claude | Gram formats inconsistent (0.50 g vs 1.1000 g) | Different decimals per screen | Shared gramsTrim formatter | Yes
DEF-12 | Medium | PM | Demo gold price (~5,526) far from the real Egypt price (~7,223) | Invented anchor price | Real 24k Egypt prices used | Yes (TC-047)
DEF-13 | Low | Claude | Calendar cell rounded values over 100 (+116 vs +115.59) | Compact formatter dropped decimals | Two decimals up to 999.99 | Yes (TC-058)

## Change Requests
ID | Date | Requester | Title | Detail | Impact | Status
DEC-1 | 2026-09-21 | PM | Funding = Aman prepaid card balance topped up via InstaPay | Phase 1 decision | Removes gateway cost; external cards out of MVP | Implemented
DEC-2 | 2026-09-21 | PM | Pricing = spread only, 0.5% per side | Phase 1 decision | Matches business case | Implemented
DEC-3 | 2026-09-21 | PM | English first, Arabic RTL later | Phase 1 decision | Bilingual strings deferred | Implemented
DEC-4 | 2026-09-21 | PM | Customer prototype only; business case presented separately | Phase 1 decision | Lab stays a separate app | Implemented
CR-BC-01 | 2026-09-21 | PM | Purchases via prepaid balance, no gateway; InstaPay top-up free | Zero gateway and top-up cost | Unit margin -0.5% to +0.5%; decision DO NOT PROCEED to VALIDATE FURTHER | Implemented
CR-BC-02 | 2026-09-21 | PM | Provider handles regulation; no outside certificates | Regulatory risk from critical to high, written confirmation gate | Risk register and decision reworked | Implemented
CR-BC-03 | 2026-09-21 | PM | CAC 250 EGP, then confirmed 10 EGP | Replaced US benchmark | LTV/CAC 0.26 to 6.5; decision to PROCEED WITH CONDITIONS | Implemented
CR-BC-04 | 2026-09-21 | PM | MVP and run team in-house, no additional cash cost | Cash share 0%; opportunity cost shown separately | Investment lines changed | Implemented
CR-BC-05 | 2026-09-21 | PM | Prepaid card live in under a month | Card risk from critical to high, not a blocker | Risk and decision text | Implemented
CR-01 | 2026-09-21 | PM | Use today's real gold price in Egypt as the example | Anchor ~EGP 7,223/g (24k) | Price service, seed, copy | Implemented
CR-02 | 2026-09-21 | PM | Minimum and step 0.1 g; no pooled model (mngm sells fractional) | Quantities in 0.1 g steps for buy and sell | Engine, validation, UI, docs | Implemented
CR-03 | 2026-09-22 | PM | Use Aman colour codes (#04768D to #64C2D3) | Palette and gradient | CSS tokens, hero cards | Implemented
CR-04 | 2026-09-22 | PM | Portfolio P&L section like the reference; click opens daily calendar | Balance card, today's row, allocation donut, calendar | New DailyPnl screen, portfolio redesign | Implemented
CR-05 | 2026-09-22 | PM | Replace demo customer data with real Sept prices and win/loss days | 20 transactions on 24 Aug-21 Sep prices | Seed, price history | Implemented
CR-06 | 2026-09-22 | PM | Remove invested vs current; add cumulative P&L chart matching the calendar | 30-day cumulative realized chart | Portfolio, chart component | Implemented
CR-07 | 2026-09-22 | PM | Calendar shows realized only, no tabs; today's cell is dynamic | Realized-only daily P&L | pnl service, DailyPnl screen | Implemented
CR-10 | 2026-09-22 | PM | Add a new-customer onboarding flow (nothing on file) and a prototype control to switch between new and existing customers | Full capture: mobile, code, PIN, details, ID, selfie, prepaid card and top-up, agreements. Control gets 3 scenarios | Onboarding, store, controls, design canvas, tickets, tests | Implemented
CR-08 | 2026-09-22 | PM | P&L card should be a daily snapshot / clarified | Periods labelled today / month / since first trade | Portfolio card | Superseded by CR-09
CR-09 | 2026-09-22 | PM | Remove the Profit and loss card to keep it simple | Card removed; details card trimmed | Portfolio | Implemented